## Register
id | action | owner | date | said_by | status | days_open | flag | record
A-01 | Reconcile July CD2 handovers: separate provisional from final (system shows 94%; treat with caution until reconciled) | Yusuf | 2026-09-04 | Yusuf | open | 13 |  | minutes
A-02 | Add available-room occupancy to the monthly pack alongside the headline figure | Yusuf | 2026-09-18 | Layla | open | -1 |  | minutes
A-03 | Spa relaunch brought forward to October (decision struck later in meeting, see A-19) | Priya | 2026-10-01 | Layla | done |  | struck | DO NOT RECORD — Layla: "Aisha, strike the October decision, the spa relaunch is Q1, unchanged"
A-04 | Produce venue exhibitor briefing pack for October medical congress (210 exhibitors) | unassigned | 2026-09-15 | James | open | 2 |  | minutes
A-05 | Confirm owner for the exhibitor briefing pack | Layla | 2026-08-28 | Layla | open | 20 |  | minutes
A-06 | Meet the traffic consultant and bring an option on east car park use (congress coaches vs leisure park Saturday overflow) | James and Noura | 2026-09-04 | Layla | open | 13 |  | minutes
A-07 | Send leisure park traffic plan drawings to James and Noura | Marco | 2026-08-28 | Layla | open | 20 |  | minutes
A-08 | Chase facilities on staff shuttle timetable (08:15 from north gate leaving at 08:10) | Noura | 2026-09-04 | Layla | open | 13 |  | DO NOT RECORD — Layla: "I'm not putting any of it in the minutes because none of it's a delivery matter."
A-09 | Chase parking permit renewal system outage | Noura | 2026-09-04 | Omar | open | 13 |  | DO NOT RECORD — Layla: "I'm not putting any of it in the minutes because none of it's a delivery matter."
A-10 | Footnote leisure park reactive maintenance tickets (up 60% due to new CMMS logging everything; like-for-like roughly flat) | Yusuf | 2026-09-18 | Yusuf | open | -1 |  | minutes
A-11 | Independent root-cause assessment of chiller three at the wave pool (failed three times since June) | unassigned | 2026-09-30 | Layla | open | -13 |  | minutes
A-12 | Speak to procurement to review the M&E contract and chiller three ticket history | Layla | 2026-09-04 | Layla | open | 13 |  | internal-only — Layla limited the notes to A-11 only: "What goes in the notes is that chiller three has recurred three times and the root cause needs an independent assessment. That's it."
A-13 | Noura's view that the M&E contractor is patching rather than replacing chiller three to protect its maintenance-contract margin | n/a |  | Noura | done |  | not an action | DO NOT RECORD — Layla: "Aisha, that last part does not go in the notes. Not the bit about the contractor's motive."
A-14 | Trial a weekday corporate package at the adventure centre, three months, marketing spend about 40,000 (within Noura's discretionary; noted, not a group decision) | Noura | 2026-10-01 | Noura | open | -14 |  | minutes
A-15 | Half-year group results figure (Daniel began to state it; no figure was spoken) | n/a | 2026-09-03 | Daniel | done |  | not an action | DO NOT RECORD — Hana: "The number cannot appear in any written note, internal or external, until it's announced."
A-16 | Segment heads to be available for investor call questions on their segments after the half-year announcement | Omar, Priya, James, Noura | 2026-09-03 | Daniel | open | 14 |  | minutes
A-17 | Circulate investor Q&A prep | Hana | 2026-08-31 | Layla | open | 17 |  | minutes
A-18 | Tell Hana anything in your segment an analyst might ask about, before the Q&A prep goes out | Omar, Priya, James, Noura | 2026-08-28 | Hana | open | 20 |  | minutes
A-19 | Decision: spa relaunch stays in Q1 as planned (relaunch budget 420,000 phased in Q1) | n/a (decision) | 2027-01-01 | Layla | done |  | decision | minutes
A-20 | Fix spa booking confirmation system setting (Marco to change it) | Priya | 2026-08-28 | Priya | open | 20 |  | minutes
A-21 | Move a staff member from the island resort to desert resort spa reception for the refurb period | Priya | 2026-09-04 | Priya | open | 13 |  | minutes
A-22 | Remove October spa relaunch from the investor narrative; replace with Q1 | Hana | 2026-09-02 | Layla | open | 15 |  | minutes
A-23 | Send draft formal response to CD2 contractor delay and disruption claim (claim value 2.4 million) to Legal | Omar | 2026-09-04 | Layla | open | 13 |  | minutes
A-24 | Issue formal response to CD2 contractor claim (28 days from receipt) | Omar | 2026-09-11 | Layla | open | 6 |  | minutes
A-25 | Send draft minutes to Layla first, not to the group | Aisha | 2026-08-27 | Layla | open | 21 |  | minutes
A-26 | Check and release minutes to the group | Layla | 2026-08-28 | Layla | open | 20 |  | minutes
Legend
Blue date = proposed by Delivery Office because the meeting gave no calendar date; confirm with owner. Hover a date for what was actually spoken.
Red rule on column G: =AND(ISNUMBER(G2),G2>0) rather than plain "greater than 0", because Excel treats the "" that a done row returns as greater than 0 and would keep it red.
Meeting date: 26 August 2026 (Group Delivery Review: August).
Formulas:
days_open = IF([status]="done", "", TODAY()-[date])
Note on D2: Spoken in meeting: "not stated". Proposed date - to confirm with owner.
Note on D3: Spoken in meeting: "August pack". Proposed date - to confirm with owner.
Note on D4: Spoken in meeting: "October".
Note on D5: Spoken in meeting: "mid-September".
Note on D6: Spoken in meeting: "Friday".
Note on D7: Spoken in meeting: "end of next week".
Note on D8: Spoken in meeting: "not stated". Proposed date - to confirm with owner.
Note on D9: Spoken in meeting: "not stated". Proposed date - to confirm with owner.
Note on D10: Spoken in meeting: "not stated". Proposed date - to confirm with owner.
Note on D11: Spoken in meeting: "August pack". Proposed date - to confirm with owner.
Note on D12: Spoken in meeting: "not stated". Proposed date - to confirm with owner.
Note on D13: Spoken in meeting: "not stated". Proposed date - to confirm with owner.
Note on D14: Spoken in meeting: "not stated".
Note on D15: Spoken in meeting: "not stated". Proposed date - to confirm with owner.
Note on D16: Spoken in meeting: "3 September announcement".
Note on D17: Spoken in meeting: "after 3 September".
Note on D18: Spoken in meeting: "Monday".
Note on D19: Spoken in meeting: "before Monday".
Note on D20: Spoken in meeting: "Q1".
Note on D21: Spoken in meeting: "this week".
Note on D22: Spoken in meeting: "not stated". Proposed date - to confirm with owner.
Note on D23: Spoken in meeting: "not stated". Proposed date - to confirm with owner.
Note on D24: Spoken in meeting: "4 September".
Note on D25: Spoken in meeting: "11 September".
Note on D26: Spoken in meeting: "tomorrow".
Note on D27: Spoken in meeting: "not stated". Proposed date - to confirm with owner.